## Gantt Chart
COMP1682 Final Year Project: 30 Week Schedule
MealMate: Condition Aware AI Nutrition Assistant
Phase | Task | Start | End | Wks | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Research and Planning | Project selection and scoping | 1 | 2
| Project Proposal | 2 | 4
| Ethical approval application | 4 | 6
Research | Literature review | 4 | 9
| Competitor analysis | 6 | 9
| User research: survey | 6 | 9
| User research: interviews | 7 | 9
Design | Requirements and MoSCoW analysis | 9 | 11
| System architecture and data design | 10 | 12
| Wireframes and user flow | 10 | 12
Development | Cycle 1: Auth, profile, body metrics | 10 | 11
| Cycle 2: Meal diary and tracking | 12 | 13
| Cycle 3: Photo recognition and barcode | 14 | 15
| Cycle 4: AI coach and safety filter | 16 | 17
| Cycle 5: Weekly plan and exercise | 18 | 19
| Cycle 6: Community, i18n, refinement | 20 | 22
Testing and Evaluation | Test plan and test case documentation | 22 | 24
| Functional and unit testing | 23 | 25
| User Acceptance Testing | 25 | 28
| SUS scoring and analysis | 27 | 28
Reporting | Report writing (continuous) | 4 | 30
| Evaluation and conclusion | 28 | 30
| Proofreading and formatting | 29 | 30
Milestones | Project Proposal submission | 4 | 4
| Contextual Report submission | 12 | 12
| Product demonstration | 22 | 22
| Final Report submission | 30 | 30
Legend
Research and Planning
Research
Design
Development
Testing and Evaluation
Reporting
Milestones
HOW TO USE THIS FILE
Blue numbers in the Start and End columns are the only cells to edit.
Bars are drawn automatically by conditional formatting, so changing a week number moves the bar.
The Wks column recalculates duration from Start and End.
Week numbers are indicative. Set them from the official university calendar.
Milestone rows are fixed submission points and should match the published deadlines.
Report writing spans week 4 to week 30 by design, mitigating risk 7 in the risk register.
To insert into the report, screenshot this sheet and add it as a numbered figure.